X:\1.TME\_TME2023\1. Jan-Feb\1. Environmental Engineering\Rich - Weston Solutions – MMRP

Words: 1196

Rich.MMRP-2

Leveraging Geophysical Technology for Military Munitions Remediation

At the formerly used defense site of Camp Croft, a large-scale complex military munitions remedial action in a densely forested, protected park used advanced geophysical classification to minimize impact on the terrain.

By Gretchen Tabano, P.E., and Caitlyn Martin, P.E.

Camp Croft served as one of the Army’s principal infantry replacement training centers during World War II, readying more than 250,000 soldiers for combat. Over its five years of operation between 1941 and 1946, soldiers were trained to use small arms, anti-tank armaments, anti-aircraft armaments, mortars, and artillery. Today, Camp Croft is a high priority Formerly Used Defense Site, encompassing 19,044-acres of the historical cantonment area and military munitions training ranges.

Situated within the site boundary is Croft State Park, a popular regional recreational destination receiving 170,000 visitors a year. Past military munitions use has created an unacceptable explosive safety risk to park workers and users. To address the possibility of exposure, U.S. Army Corps of Engineers (USACE) Savannah District; U.S. Army Engineering and Support Center, Huntsville; and Weston Solutions are implementing a multi-year Military Munitions Response Program remedial action to address munitions and explosives of concern (MEC) within the Project 07 Munitions Response Site, which encompasses over 1,277-acres of Croft State Park.

To achieve the project’s remedial action objective, cutting-edge geophysical detection and positioning technologies are being used at an unprecedented scale and under challenging site conditions. Deliberative technology selection, enhancements, and deployment are necessary to balance the needs and expectations of the state park land manager while putting to action contemporary Department of Defense emphasis to use advanced geophysical classification (AGC) at Formerly Used Defense Sites to the extent possible.

LEVERAGING GEOPHYSICAL TECHNOLOGY

The rolling, densely forested terrain at Croft State Park is a natural resource coveted by the local community and a popular destination for outdoor enthusiasts. Mature and other specific tree species within the park cannot be cut and must be avoided per the land manager’s requirements. A number of former homesteads, cemeteries, and other culturally significant sites dot the landscape and must be protected.

Previously, analog geophysical methods would be the preferential approach for munitions remediation at this type of site. Use of analog technology is more efficient over difficult terrain and helps maintain a natural landscape by limiting the amount of vegetation removal required. However, analog geophysics would not achieve the established project remedial action objective; thus, AGC was considered as the approach for munitions detection and removal.

AGC technologies provide the ability for trained analysts to decide whether a buried metal object has the characteristics of military munitions and requires excavation, or if it is metallic debris that can be left safely in place without intrusive investigation. AGC can significantly reduce investigation efforts by focusing resources on detecting and excavating only the items that have potential explosive safety concerns.

Often implemented as a two-phase approach, geophysical sensor operators collect full coverage mapping data to locate buried metallic objects, followed by static measurements at each detection location to provide geophysical data necessary to make classification decisions. Due to the size and remoteness of the site, and the contracted performance schedule, project execution at Croft State Park required creative use of new and emerging AGC technologies to reduce impacts to public recreation and meet project completion dates.

Park use and natural balance will always be contributing factors to remedial design at formerly used defense sites like Camp Croft. However, effectively executing the remedy to meet the remedial action objective is exponentially more complicated with the increased importance of collecting robust, high-quality, and defensible AGC data, regardless of the site conditions.

CAREFUL DEPLOYMENT

For Croft State Park, White River Technologies’s APEX system was selected for use. APEX is an AGC sensor that collects the data necessary to make classification decisions in one pass and eliminates the need for static measurements at each buried item location. A total of six APEX systems, the first large scale deployment of its kind, have been in operation at the site since February 2021.

APEX’s dynamic AGC deployment in the complex environmental conditions around Croft State Park entails extraordinary startup and site preparation activities. Working within protected, closely spaced mature growth trees requires careful manual and mechanical vegetation reduction. Proof-of-concept demonstrations of the process were witnessed and approved by park officials prior to full-scale implementation.

All work is designed to maintain the health of the forest and natural landscape during and after remediation. Undergrowth is surgically removed to the ground surface to provide safe access for the APEX units to meet quality and performance goals. A network of geodetic survey control points spaced at 100-ft increments across the site is necessary due to tree density and topography. Conventional ground survey stake-out methods were required due to tree canopy and topographic terrain that prohibited the use of GPS. Nearly 3,100 control points established by surveyors ensure that geophysical data is accurately positioned and repeatable to centimeter-level accuracy. The control network was also originally used by field teams for navigation and positioning with robotic total station instruments that provide automated optical electronic distance measurements through line-of-sight.

Because the state park land manager prohibited extensive tree removal, the density of the remaining trees minimized the efficacy of robotic total station positioning due to line-of-sight restrictions. When integrated with APEX, robotic total station positioning greatly impaired geophysical survey production rates and limited coverage around trees and topographical obstacles where optical tracking was impossible. To increase overall performance, a series of site-specific integration tests were performed with new simultaneous localization and mapping (SLAM) technology developed by KAARTA and originally piloted by USACE’s Environmental and Munitions Center of Expertise.

KAARTA’s Stencil uses the SLAM process for positioning. A high-precision 3D laser point cloud can be rapidly collected, allowing the device to determine location without the need for line-of-sight or satellite connectivity. SLAM technology combined with APEX allows field teams to collect AGC data around trees while maintaining a constant positional data stream, resulting in an immediate boost in production rates. Over the last two years, the project has completely transitioned from robotic total station to SLAM for all APEX units, increasing survey production by 200 percent.

SPEED AND QUALITY

Progressive and adaptable approaches to innovative technology integration have been key to providing an efficient remediation solution with minimal impacts to park visitors. The willingness of the project delivery team to consider and ultimately accept the use of the latest AGC and positional technologies has enhanced the overall quality and performance at Croft State Park.

Remediation efforts are approximately 60 percent complete, with fieldwork anticipated to be completed in June 2024. More than 87,900 buried metal detections have been encountered, and by using AGC, a total of 11,500 locations have been determined to require excavation. This 88 percent reduction in excavations significantly reduces overall project schedule but, more importantly, limits impacts to the park resources and surrounding environment.

To date, 5,300-lbs of munitions debris and 11 MEC have been safely located and removed, including three MK II Hand Grenades; one M49 Trip Flare; four 60-mm M49 HE mortars; two M17A1 Rifle Grenades – Flare; and one M1 fuze.

The work completed showcases how the integration of new technologies can provide more efficient, high-quality results, facilitating the goal of ensuring a safer recreational area for park users for generations to come. This approach is being evaluated for use at other closed military ranges and is expected to aid in data collection efficiencies while also improving quality.

Gretchen Tabano, P.E., is Senior Project Manager, and Caitlyn Martin, P.E., is Project Engineer, Weston Solutions. They can be reached at Gretchen.Tabano@WestonSolutions.com and Caitlyn.Martin@WestonSolutions.com.

PHOTOS

Rich.MMRP 1.jpg

Due to densely wooded conditions at the formerly used defense site Croft State Park, advanced geophysical classification technology was used to detect and remediate buried munitions.

Photos courtesy Weston Solutions

Rich.MMRP 2.jpg

Through the use of advanced geophysical classification technology, required excavations have been reduced 88 percent, limiting the impact on the park’s environment.

Rich.MMRP 3.jpg

Simultaneous localization and mapping technology generates positional data to navigate within a precise 3D point cloud without line-of-sight and satellite connectivity.